PRIORITY AXIS 1: Innovative and socially responsible Danube region

INVESTMENT PRIORITY 1b: Promoting business investment in R&I, developing links and synergies between enterprises, research and development centers and the higher education sector

SPECIFIC OBJECTIVE 1.2.: Increase competences for business and social innovation

CONTEXT

When compared with the whole European Union, the Danube region (besides Germany and Austria) is facing a problem with the innovation and innovative economic solutions, especially on the level of small and middle sized enterprises. The problem is multi-sided and it has expanding numerous effects. One of them is development which is positively correlated with the level of innovation: the more innovations, higher the growth and development.

Promoting innovation and technology in SMEs would enhance their competitiveness and would promote innovation-based development – which would tackle lagging innovation and economic performance in the region in recent crisis years. Studies show that those companies who prioritise innovation are also those who experience the highest increase in turnover (Innobarometer, 2014). Some 79% of companies that introduced at least one innovation since 2011 experienced an increase of their turnover by more than 25% by 2014.

TARGET GROUPS

This project would be specifically aimed on manufacturing SMEs which use machine equipment (in production) eligible for technological upgrade and enhancement.  Besides problems with gaining more innovative methods of production, many of manufacturing SMEs have the issues regarding the production of innovative products that would make those companies more competitive on the European and global market.  The smaller the company is, the more it faces constraints to innovation or to the commercialisation of its innovations. According to the EU data:  around 63% of companies with between 1 and 9 employees declared having introduced at least one innovation since 2011, compared to 85% of companies with 500 employees or more; also, around 71% of companies with between 1 and 9 employees encountered difficulties commercialising their innovations due to a lack of financial resources, compared to 48% of companies with 500 employees or more.

Therefore, small and medium-sized enterprises (SMEs) should be a particular target for innovation policy. The competitiveness and level of business quality is interlinked with innovative products, i.e. the level of innovative production depends on the number of innovative incentive inputs that company utilizes to increase the quality of their business (in our context this includes inputs such as ideas emerged from cooperation and networking between SMEs and academic sector).

The Danube region holds vast potential for commercially exploitable technology-based resources.

This potential of the Danube region is also recognized by the EU: “the actions coordinated by the EU’s DG Research and Innovation include enabling universities, research centres and businesses to exploit their full innovation potential including capacity building actions promoting interregional and international collaboration and preventing brain drain in thr Danube region” (Panorama Inforegio, The EU Strategy for the Danube Region (37), Spring 2011: 20). There are two main reasons for this. First of all, the technologically enhancing effect could be found in the high educational sector (professors, students and associates linked with universities).

Students and experts from technical universities and with innovation orientation could provide fresh and innovative solutions to SMEs, only if there were a stronger link between academic and business sector. By giving the opportunity and knowledge to both sides we could create a linkage of technology-innovation transfer toward SMEs with huge commercial potential, because innovation feeds business and vice versa. Secondly, the Danube region is lagging behind the average of the EU in innovation performance (except the south of Germany, Austria and Slovenia); therefore, other below-average countries in the region would benefit from the cooperation, which is predicted in this project, with leading innovators in the region. Most importantly, this would promote growth and development of the region and subsequently of the EU.

This solution isn’t only fostering innovation in the manufacturing SME business sector which is always looking for new solutions, but, moreover this kind of bondage is a way to decrease the EU diversity regarding innovations.

The way to achieve this goal is to act on international and intersectoral level – by connecting two obviously complementary sectors (academic and business) in the region.

Within the created web platform and app, the innovation will be promoted and the effects of this result will be multiple benefit for all EU member states. By creating more favorable conditions through e.g. innovative support measures in the frame of the INNJECT project, that contributes to the creating and maintenance of more solid linkages among the SMEs and academia, we could create a linkage of technology transfer with huge commercial potential for innovation, because innovation feeds business and vice versa.

OVERALL PROJECT OBJECTIVE: Strengthen cooperation among manufacturing SMEs and high education sector in order to foster better transfer of technologies in commercial purposes

Specific objective 1: Fostering innovation of manufacturing SME sector for better utilization of innovative technologies through series of educational transnational activities

Specific objective 2: Raising the level of awareness among high education sector about the potential of market based innovations and technologies

Specific objective 3: Ensuring long-term support web platform and collaborative online tool for better transfer of knowledge, technology and ideas among target groups

WORK PACKAGES

| # | NAME | DESCRIPTION | ACTIVITIES | OUTPUTS |
| --- | --- | --- | --- | --- |
| WP1 | Project management | This work package will be related to the setting up the management structure board of the project. To this board will be assigned responsibilities and clear decision making structure procedures. Decision making process will be carried out by Steering Committee (SC). SC is composed by representatives of each partner and leaded by the Project Manager by Lead partner, responsible for the project overall organization. The SC will meet every 6 months. SC will adopt “Project manual” which will contain internal procedures for decision making and project management quality criteria. LP will act as the interface between the Programme (MA, JS) and the partnership. LP will with the project partners share responsibilities and contributions to the work plan and activities, reporting requirements, financial provisions etc | Managament team will be structured by three key positions: Project Manager (PM): in charge with the overall management and coordination of the project implementation, daily monitoring of project progress with the support of Work Package Leaders and Activity Leaders, compilation of the content parts of the Progress Reports and timely submission thereof, achievement of project objectives within the planned period of time and quality control of delivered outputs. He/ she also acts as an interface between Joint Secretariat and the partners Financial Manager (FM): responsible for permanent monitoring of all financial aspects, including internal management of funds, expenditures, spending rates, budget shifts, financial reporting, public procurements, collection of documents for the Controllers Communication Manager (CM): responsible for developing and implementing project communication strategy, defining communication objectives, approaches, activities and key messages to be sent out, preparation of information materials and promotion items, preparation and distribution of newsletters and press releases to identified stakeholders. The Communication Manager will also coordinate communication within the partnership by setting up internal communication rules and monitoring tools, updating the information on the project section in the DTP website etc.The core management team will also act as permanent contact for external actors. Similar positions as the ones mentioned above should also exist at partner level so that specific issues can be dealt with in a more efficient way. | Lead applicant will put in charge individuals who will be in charge for proofreading, analysing and reviewing project outputs from the qualitative point of view and submission of quality reports. External written validation of project outputs will be organized by the Lead partner. |
| WP2 | Communication activities | This WP includes development of communication strategy which will consist described general goal and objective for the project’s communication, the addressed target groups, the main communication activities, related budget and partners tasks among themselves. | Project Communication Plan will be developed in close cooperation with the project coordinator and project partners. All partners will be involved and committed in the communication activities. Communication manager task will be implementation of the Communication Plan and distribution and involvement of all partners in communication activities. This person will be connected with Joint Secretariat. For internal communication there will be created “Central storage” which will ensure fluent communication among partners. | Deliverables of this WP includes: Communication strategy and Communication plan; Press conference, releases and articles; Informative materials; 20 awareness events (4 per each PP); Communication training (once per year according to the needs); Lead partner seminar (only once after the project´s approval). Partner Bulgaria Economic Forum will be responsible for setting up the whole communication system developing the communication strategy and materials. |
| WP3 | Transferring and adopting educational tools and methods for manufacturing SMEs | This work package includes transnational cooperation between included project partners in order to create a map of manufacturing SMEs and develop an action plan and education system for better utilization of innovative technologies | 3.1. Detecting manufacturing SMEs, their needs and demands in the terms of using technology, technological problems and knowledge about use of innovative technologies 3.2. Creating a strategy that includes educational action plan with detailed learning curricula about using innovative technologies in their businesses 3.3. Summarizing and identifying common areas in the individual strategies for long - term cooperation 3.4. Implementing action plan - informal, educational, learning courses for machinery based SMEs 3.5. Creating common evaluation document among partners which will represent a base for future INNJECT app platform | The outputs will be: 50 detected SMEs per every included country, with analyzed technological and educational needs; Strategy plan per each included country will be created; one Joint strategy plan will be created; Action plan per every country will be implemented (5 educational courses per country) and common evaluation document will be created; one common evaluation document among partners will be created. General needs of target group will be detected. |
| WP4 | Stimulating network between included target groups | This work package will establish the initial contact between the target groups and create starting collaboration point based on common learning and educational activities. | 4.1. Introducing experts and students from technological departments from academic and scientific sector with the possibilities of collaboration with manufacturing SMEs by presenting common evaluation document (in every country) 4.2. Building joint educational methods for experts and students with the aim of introducing them with proper needs of SMEs 4.3. Implementing 3 educational models for experts and students in every country 4.4. Creating a common Learning Intervention document 4.5. Organizing study visits by presenting the best practices to SMEs and experts and students | Outputs will be: 10 introduced and educated experts and students per each country with 3 educational, common models created and organized by PP; one common Learning Intervention document will be created; 6 study visits were organized and target group is familiar with possible collaboration. |
| WP5 | Implementing and adopting of innovative tools | This work package includes creating of concrete measures and online-based tools for international and multisector cooperation of target groups as well as public presentation of final results, i.e. the aforementioned tools. | 5.1. Researching and developing a new document - „Technological radar“ with the aim of exploring which technologies are necessary for detected needs of SMEs, which technologies are available and which technologies need to be developed 5.2. Exploring the possible ways, best practices, ICT tools and IT experts with the aim of creating INNJECT web and app 5.3. Creating of one common INNJECT web and app that includes all the information about needs and demands of included SMEs as well as list of students and experts who are offering their technological solutions and knowledge. 5.4. Presenting tools to the target group in every included country 5.5. Organizing transnational conference for presenting best practices, networking and presenting the innovative tools. | The output will be: common document „TECH radar“; created and presented INNJECT app and web portal; transnational conference will be organized. |
| WP6 | Testing the innovative solutions with practical implementations | The final work package consists of pilot implementations of the developed online tool and dissemination activities between the project partners. | 6.1. Organizing of pilot actions by stimulating the collaboration between actors in every PP country 6.2. Presenting the results of collaboration between actors in every PP country 6.3. Measuring the results and upgrading the INNJECT app | The output will be: minimum 3 new collaboration between SMEs, experts and students; 3 pilot actions or new/upgraded product /service; results will be presented by each country and target group and results will be measured and upgraded. |

LINKS TO EU STRATEGIES AND PROGRAMMES

European Union strategy for Danube region

The INNJECT project is tackling some of the challenges stated in the communication document of the European Commission for the Danube strategy, especially the challenges regarding the socio-economic situation: “the Region has very wide disparities. It has some of the most successful but also the poorest regions in the EU. In particular, contacts and cooperation are often lacking, both financially and institutionally. Enterprises do not sufficiently exploit the international dimension of marketing, innovation or research.” Also, the INNJECT project is leaning on two of four pillars of Danube strategy Action Plan – Building prosperity in the Danube Region and Strengthening the Danube Region, targeting some of the main issues: Education & skills, Research & Innovation, Enterprises, Employment market and Institutional capacity and cooperation.

Europe 2020

The INNJECT project is in line with Europe 2020 strategy and its first priority Smart growth – developing an economy based on knowledge and innovation which means that knowledge and innovation must be drivers for Europe’s future growth. This requires improving the quality of our education, strengthening our research performance, promoting innovation and knowledge transfer throughout the Union, making full use of information and communication technologies and ensuring that innovative ideas can be turned into new products and services that create growth, quality jobs and help address European and global societal challenges. It means that Europe must invest in innovation and R&D, education, training and lifelong learning, and in Europe as a digital society.

EU2020 initiatives

The INNJECT project is in correlation with several initiatives under the Europe 2020 strategy: "Innovation Union" (to improve framework conditions and access to finance for research and innovation so as to ensure that innovative ideas can be turned into products and services that create growth and jobs); "Youth on the move" to enhance the performance of education systems and to facilitate the entry of young people to the labour market; "An industrial policy for the globalisation era" to improve the business environment, notably for SMEs, and to support the development of a strong and sustainable industrial base able to compete globally; "An agenda for new skills and jobs" to modernise labour markets and empower people by developing their of skills throughout the lifecycle with a view to increase labour participation and better match labour supply and demand, including through labour mobility.

The Territorial Agenda of the European Union 2020 is an agenda under the Europe 2020 Strategy which helps with implementation of actions of EU2020.

SE2020

The INNJECT project with its goals is in line with goals of the South-East Europe 2020 Strategy (SEE 2020) which tends to improve living conditions in the region and bring competitiveness and development back in focus, closely following the vision of the EU strategy Europe 2020. The Strategy is based on 5 pillars and the project correlates to four of them: Smart Growth: by committing to innovate and compete on value-added rather than labour costs; Sustainable Growth: by raising the level of competitiveness in the private sector, development of infrastructure and encouraging greener and more energy-efficient growth; Inclusive Growth: by placing greater emphasis on developing skills, creating employment, inclusive participation in the labour market and health and wellbeing; Governance for Growth: by enhancing the capacity of public administration to strengthen the rule of law and reduce corruption, the creation of a business friendly environment and delivery of public services necessary for economic development.

The project is also in correlation with some other strategic documents:

- SME Small Business Act for Europe (improving the approach to entrepreneurship in Europe, simplify the regulatory and policy environment for SMEs, and removing the remaining barriers to their development)

- The Danube Innovation Partnership (aims to support the acceleration of technology transfer and research commercialisation in the Danube area)

- Western Balkan R&D Strategy for Innovation (the Strategy aims to strengthen the region’s research capacity, enhance intraregional cooperation, promote collaboration with business sectors, explore possibilities for financing R&D from EU funding schemes and other external sources, and help integrate the region into the European Research Area (ERA) and Innovation Union)

LINKS TO GOOD PRACTICES

INNJECT  project would be a continuation of the EU's tradition to support  innovation and enterprenuership in the Danube region. There are many projects which had similar general goal as the INNJECT project within previous South-East Europe Transnational Cooperation Programme. Just to mention a few examples of past efforts and existing knowledge on which our project would be based: InterValue, SEET and AUTOCLUSTER.

InterValue was a meta-repository of R&D results and a collaborative web-space facilitating the interaction between researchers, companies and experts, and supporting innovation by academic research.

The Platform was aimed at guiding and supporting the processes of collection, elaboration of detailed valorisation plans, and commercialisation of research results.  Further,  SEETechnology  project was aimed at improving and developing support services to innovative SMEs provided by university based SME-support centres and science parks in order to facilitate the take-up of research ideas and products through better access to knowledge, resources and markets locally and at transnational level. The project tackled this issue due to the fact SMEs in the SEE region are especially weak in terms of innovation and access to innovation, there is a mismatch between the supply and demand of research products at local/regional/transnational level, and university connected science park lack resources and knowledge and do not work closely with SMEs. Third project which represents the tradition of supporting innovation and SMEs was AUTOCLUSTERS project was aimed at bringing together Universities, R&D institutions, SME support facilities from EU-15, NMS as well as IPA to prepare and create first Automotive network in SEE. The second level clustering activities proposed by project are strictly oriented on the activities they are improving the innovation capacities in region and improve technology and know-transfer improvement the innovation circle.

INCLUDED PROJECT PARTNERS (so far)

LEAD PARTNER: TOB Burgenland (Austria)

| # | Partner name | Country |
| --- | --- | --- |
| 1 | Development agency North | Hungary |
| 2 | Bulgaria economic forum | Bulgaria |
| 3 | Koprivnički entrepreneur Ltd. | Croatia |
| 4 | DEX Innovation Centre | Czech Republic |
| 5 | Faculty of Technology Novi Sad | Serbia |
| 6 | RAZ:UM | Slovenia |
| 7 | Germany ??? |  |